# BTE June 2025 Project Updates

# Tangential Flow Filtration (TFF) Project

Workstream Overview:

(Press the paragraph button   in the menu above to see the workstream overview. I’ve hidden it for space)

The objective is to finish development a scalable TFF platform suitable for 90% of products going into IDB. It must incorporate two or fewer modules for clinical supply which requires a capacity of >500L/m2. Cycle 2 and 3 and commercial requires 4 or fewer modules per 2000L perfusion by December 2025 which requires a capacity of >1000L/m2.

- 1000L/m2 at bench scale for cycle 2/3 molecules in 2025

- Cycle 1 molecules for 500L/m2 capacity

- Two molecules at 50L or greater with 1000L/m2 by Dec 2025

- Three 500L runs will use rTFF in 2025 for 2936. One will have >1000L/m2 in 2025.

Recent Progress:

- completed AZD2936 cell culture study to look for alternative filter vendors. Waiting for analytical data

- demonstrated that ambr250 can be adapted to use filters other than Repligen

- demonstrated online osmo control using Raman (Aug / Sep2025)

Challenges:

Next Steps:

Priority Level:

High priority due to critical upcoming decisions regarding membrane selection and process optimization.

Action Items for Bill (Boss):

# Perfusion Platform

Project Overview:

The goal is to develop a platform perfusion process that accommodates 90% of molecules moving into IDB and aims to produce five times more material than a typical fed-batch process.

Regular 5x productivity will be assessed by showing the IVCV is 5x that of the average fed-batch IVCV when a project does not have fed-batch information

The platform will cover a bioreactor control strategy, media formulation, and TFF (handled separately due to urgency and risk).

Stretch Goal:

- Control PQ during dynamic perfusion such that any sub lot would be releasable

- Control PQ for pooled batch such that the statistics make it impossible for competators to make without a feedback PQ control strategy

Recent Progress:

Challenges:

Next Steps:

Confirm cell-specific productivity at low perfusion rate and low osmo.

Priority Level: High

PROJECT 2936: High

Concentrated media: Medium

Action Items for Bill:

# Rilveg (2936) Downstream

Project Overview:

The aim is to adapt the fed-batch 2936 process to the IDB downstream with minimal changes while leveraging PMI-reducing techniques used in other products to reduce the downstream PMI by 10% from platform by July 2025. The formulation should achieve 200g/L on average. The UFDF will be implemented. The Asymmetric Dialysis should have solid small and pilot scale data by the end of the year running 1-5 kg of material.

Recent Progress:

Challenges:

Next Steps:

Priority: High

# 5x25 Downstream Project

Project Overview: Evaluate the performance of the lead affinity reagent in conditioned media and elution steps

The ultimate objective is to develop a downstream process that uses at least 50% less water and can maintain a cost of goods manufactured (COGM) of $10/g overall for high titer monoclonal antibodies (mAbs). Approximately $2/g is allocated for consumables and raw materials for the downstream process.

This year, we want to show for two mAbs:

- Affinity precipitates and >10 LMH at >10g/L for a capacity of >240 L/m2 (i.e. 24 hours operation before cleaning) by August 2025

- Show affinity precipitates can be washed to theoretically provide 2 logs of clearance of non-bound impurities by August 2025

- Show precipitates can be dissolved, and the mAb recovered with 80% yield overall, and <5% affinity moiety in purified mAb by December 2025

Stretch goals

- Demonstrate the precipitation, wash, and elution with CM containing material, achieving 2LRV of HCP and DNA for one mAb

Recent Progress:

Challenges:

Analytics

- Presence of the affinity reagent in the mAb pellet samples introduces variability in platform HCP quantitation methods; the work-around is to find the working range for diluted samples.

- Presence of the dextran in elution samples interferes with the custom low pH SEC method; in the meantime employ SDS-PAGE for semi-quantitative sample analysis

Next Steps:

# Commercial equipment and plant design

# GPF North equipment and engineering runs

# Asymmetric Dialysis Platform

Project Overview

Move asymmetric dialysis to the point of being a regular part of the platform. IFB is considering it as well.

Priority Level: High

# MAST: Modeling, AI, Simulations, and Twins

Lead by Nick Guros, Maryam Pouryahya, James Savory

Project Overview:

The BTE portion of the project is focused on providing digital twins to the IDB process to

- Control the bioreactor

- Indicate when to switch the TFF and other membranes, as well as predict how long the filters have left

- Calculate load on the chromatography

- Evaluate chromatograms to determine if the column has degraded to an unacceptable level

- Calculate step yields in real time

- Indicate when in-line downstream pH probes need single—point calibration

- Provide management a dashboard for the run

Recent results

Challenges

Action Items for Bill:

Support the efforts

Priority: High

# Sustainability Project

Carbon Target Framework: within AZ, the purpose is to test a tool that can be used in development to guide development to making processes that have less carbon utilization. AZ upper management has chosen software which is called internal to AZ: “LCA LITE.”

NIIMBL demonstrated a Biopharmaceutical focused LCA Lite tool (they called it the same thing!) that we can use. It is more likely to be of immidate use to us than the AZ LCA Lite tool, which is focused on Synthetics (but does not yet work for synthetics).

EcoPharm: The purpose of Eco pharm is a British government, academic, industry partnership focused on increasing sustainability in the pharma sector.  They have seven workstreams, one of which is biologics. We are participating in reviewing proposals and workstreams in the biologic category. I understand that AZ is a founding member. We need to attend meetings and recommend projects. We can count many of our sustainability work toward in-kind contributions.

Priority: medium

# IP Collaborations