## Slide 1: NGM Steering Committee Update
May Update
Company Restricted
27May2020

## Slide 2: 2020 Deliverables/ Milestones
1Q2020
2Q2020
3Q2020
4Q2020
Phase 1: Engineering firms proposals- complete
Phase 1: Engineering firm selection- Jan/Feb
High Level Timeline for IMFINZI NGM Strategy
NGM GPF Fit Gap Assessment (500 K)
Begin design of downstream equipment for 2kL scale
CMO search completed; begin discussions on implementing 1-2kL perfusion and integrated DS
Phase 2: Engineering study finalized (Timing TBD)
Complete design of downstream equipment for 2kL scale
GPF bioreactor automation
6389 Process Lock
IMFINZI NGM Process Development start
Full business case approved
6570 NGM Decision
Complete GPF TT for 6389
RFP for 2kL scale system
Award 2kL scale system to manufacturer
6570 Cycle 2 start
3X NGM Process Platform Defined
Legend
On-Track
At- Risk
Late/ Off Track
Complete
Feasibility Study
COGM Model
CMO search initiated
Phase 1: Engineering study finalized
Product Strategy for NGM Portfolio
Interim business case completed: secure 2021 funding
DSC bioreactor automation
GLP Tox for 8887
GLP Tox for 7745
Super stretch: GLP tox for 4893

## Slide 3
3
Steering Committee Update:
Next Generation Drug Substance Manufacturing
3
Progress Since Last Update:
Feasibility Study (Capital to establish capability)
Product Strategy (Timeline and Volume) for LifeCycle and Pipeline Products (MEDI6570, MEDI5752, MEDI7352)
COGM Model
NGM Data for MEDI6570 and 6839
RFI submitted to CMOs
Technical Challenges
None
Escalations
None
Upcoming:
NPC Calculation to support Interim Business case
CMO Selection for RFPs
Pam Review (Focus for Today)
Notes: * NGM Sin